## Sheet1
SPRINT BACKLOG
ID | Backlog task | Assigned to | Start Date | End Date | Priority | Status | Change management notes | Initial estimate | Day 1 | Day 2
1 | As an admin I want to be able to access the menu So, I can add items to the menu | Seayar |  |  | Top
| Design |  | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI |  | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality |  | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
2 | As an admin I want to be able to access the menu So, I can update the menu | Seayar |  |  | Top
| Design |  | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI |  | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality |  | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
3 | As an admin I want to be able to access the menu So, I can delete items from the menu | Seayar |  |  | Top
| Design |  | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI |  | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality |  | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
4 | As an admin I want to be able to access customers list So, I can see the list of registered customers | Manizha |  |  | Top
| Design |  | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI |  | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality |  | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
5 | As an admin I want to be able to access customers list So, I can delete customers from the list | Manizha |  |  | Top
| Design |  | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI |  | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality |  | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
6 | As an admin I want to be able to access raw materials list So, I can add raw materials to the list | Maihan & Khalid |  |  | Top
| Design | Maihan | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI | Maihan | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality | Khalid | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
7 | As an admin I want to be able to access raw materials list So, I can delete raw materials from the list | Maihan & Khalid |  |  | Top
| Design | Maihan | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI | Maihan | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality | Khalid | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0
8 | As an admin I want to be able to access raw materials list So, I can update raw materials in the list | Maihan & Khalid |  |  | Top
| Design | Khalid | 27/3/2021 | 28/3/2021 |  | Progress |  | 2 Days | 0 | 0
| UI | Khalid | 27/3/2021 | 28/3/2022 |  | Progress |  | 2 Days | 0 | 0
| Functionality | Maihan | 27/3/2021 | 28/3/2023 |  | Progress |  | 2 Days | 0 | 0
| Testing |  | 27/3/2021 | 28/3/2024 |  | Progress |  | 2 Days | 0 | 0